University Vision

Bowling Green State University (BGSU) aspires to be a premier learning community, and a national model, for developing individuals and shaping the future through learning, discovery, collaboration and personal growth.School of Art Vision

The School of Art aspires to be a global contributor to visual arts education, research and practice. We strive to broaden our students’ worldview in professional, creative and social aspects of technology and practice. We aim to create a transformative environment that produces artist/scholars who are leaders in their disciplines and communities.

Mission

Bowling Green State University (BGSU) provides educational experiences inside and outside the classroom that enhance the lives of students, faculty and staff. Students are prepared for lifelong career growth, lives of engaged citizenship and leadership in a global society. Within out learning community, we build a welcoming, safe and diverse environment where the creative ideas and achievements of all can benefit others throughout Ohio, the nation and the world.School of Art Mission

The School of Art at Bowling Green State University embraces the dialog between progressive and critical reflection, and craft-based practices. We serve as a catalyst for individual and cultural growth by fostering discourse, action, collaboration and creativity. Our community supports students and faculty to study and produce art within an interdisciplinary perspective that is historically and culturally informed, and responsive to contemporary social, environmental and ethical issues.

University Strategies

- Create distinctive coherent undergraduate learning experiences that integrate curricular and co-curricular programs.

- Expand the student populations for BGSU enrollment and implement programs to recruit and retain them to successful program completion.

- Identify and pursue economic development and curricular engagement opportunities.

- Enhance institutional capabilities for research and creative achievements.

- Realign individual and institutional incentives and resources to support institutional priorities.

- Adapt institutional processes and resources for attracting new faculty and staff and for promoting the development of their talent and contributions.

- Increase institutional diversity and inclusion through communication of benefits.

School of Art Goals

1. Develop a model arts environment.

2. Advance faculty and student achievement

3. Strengthen partnerships.

4. Increase communication and visibility.

5. Grow awareness and use of technologies in art practice and scholarship.

6. Expand integration of social, environmental and ethical issues

SUMMARY OF PLANNED ACTIONS

| Identified Actions (In order of priority) | Related Strategies | Resources Needed | Action Timeline | Responsible Party | Measure Index(es) | Review Feedback |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Obtain NASAD ten year reaccreditation |  |  |  |  |  |  |
| Conduct successful NASAD accreditation visit in spring 2012 | USO 7; U 1-7; A&S 1,2,3; A1-7 | Facilities, faculty and staff support as below | AY 2012-13 | Director, Dean, Provost, CFO | ART 1, 2 |  |
| 2. Strategically rebuild faculty |  | None | AY 2012-16 | Faculty and businesses |  |  |
| Replace vacant tenure-track assistant professor line in art education with untenured associate professor line | USO 2,6; AS 1,2,3; A 6 | $60,000 | AY 2013-14 | Dean, Provost |  |  |
| Replace vacant graphic design tenured professor line with tenure-track graphic design professor line. | USO 2,6; AS 1,2,3; A 6 | $55,000 | AY 2013-14 | Dean, Provost |  |  |
| Replace vacant 3D studio tenured professor line with tenure-track studio/practitioner/critic in intermedia | USO 2,6; AS 1,2,3; A 6 | $50,000 | AY 2014-15 | Dean, Provost |  |  |
| d. Replace vacant 2D studio tenured professor line with tenure-track studio/practitioner/critic in intermedia | USO 2,6; AS 1,2,3; A 6 | $50,000 | AY 2014-15 | Dean, Provost |  |  |
| Convert existing instructor line to tenure-track assistant professor in contemporary art history/theory | USO 2,6; AS 1,2,3; A 6 | $50,000 | AY 2015-16 | Dean, Provost |  |  |
| Convert existing instructor line into visiting scholar/artist/critic | USO 2,6; AS 1,2,3; A 6 | $25,000 per semester | AY 2015-16 | Dean, Provost |  |  |
| Retain existing instructors in all areas/divisions if enrollments permit | USO 2,6; AS 1,2,3; A 6 | Retain existing | AY 2013-16 | Dean, Provost |  |  |
| 3. Recruit to selectively grow student numbers in undergraduate and graduate programs |  |  |  |  |  |  |
| Grow School of Art enrollments to about 750-800 if resources remain stable; Attend more national portfolio review days; make high school visits | USO3,5,7,17 AS 1,2,3; A2 | None – School of Art and Admissions | AY 2012-17 | Dean, VP for Enrollment Management |  |  |
| Partner with other campus units to create and sustain two assistantships in MA and MFA | USO 3; AS 1, 2, 3; A 1, 4 | None – existing funds | AY 2013-14, ongoing | Dean, Graduate College, campus units |  |  |
| c. Reactivate MFA in Graphic Design, targeting self- funded students | USO 2, 5; AS 1, 2, 3; A1, 2 | $5,000, recruitment materials | AY 2013-14 | GD faculty, School, Director, Dean, Provost |  |  |
| d. Investigate post-baccalaureate, including summer classes, targeting self-funded students | USO 3; AS 1, 2, 3; A1, 2 |  | AY 2013-15 |  |  |  |
| Contribute to University’s and Arts and Sciences recruitment, retention and graduation rates | USO3,5,7,17 AS 1,2,3; A2 | $20,000 half of undergrad advisor | AY 2014-15 | Admissions, Assistant Dean, |  |  |
| Create scholarships for under-represented groups | USO 7, A 2 | $100,000, devt. staff | AY 2014-16 | Director, donors |  |  |
| 4. Build innovative curricula |  |  |  |  |  |  |
| a. Create Intermedia curriculum | USO1,2,6; A1,2,5,6 | See above re hires | AY 2013-15 | Faculty, Director, Dean, |  |  |
| Establish donor fund for team teaching, one class per semester | USO 5; A2,3 | $75,000 | AY 2013-15 | Director, Dean, Office of Development |  |  |
| c. Add contemporary art/criticism/theory class for all majors | USO 1,4,6; A1,2,6 | See above re hires | AY 2013-15 | Director, Dean, Provost |  |  |
| Support faculty development for teaching with technology | USO 1,2,4; A1,2,5 | See above re hires | AY 2013-18 | Director, Dean, Provost |  |  |
| h. Expand curricular cultural diversity requirements | USO 7; A 1, 6 | No cost | AY 2012-18 | Director, Dean, Provost |  |  |
| e. Expand immersive learning: Study Abroad | USO 1; A1,2,3 | $750,000 endowment | AY 2012-15 | Director, Dean, Provost, International Programs |  |  |
| f. Expand school-wide field trips – four per year | USO 1; A1,2,3 | $250,000 endowment | AY 2012-18 | Director, Dean, Office of Development |  |  |
| g. Create online learning communities | USO 1,2; A1,2,3 | Fee for release time | AY 2012-18 | Director, Dean, Provost |  |  |
| h. Expand curricular cultural diversity requirements | USO 7; A 1, 6 | No cost | AY 2012-18 | Director, Dean, Provost |  |  |
| 5. Improve physical space, facilities and equipment |  |  |  |  |  |  |
| Renovation of old wing of the School of Art and associated naming of School of Art; if not possible then 5.b, 5.c, 5. d and 5. E | USO 1, 4, 6, 8; A&S 1,2,3; A 1, 4 | $6.5 million One-time dollars | AY 2012-15 | Capital Planning, A&S Dean, Donors |  |  |
| b. NASAD accreditation-related relocation of jewelry/metals studios and first year | USO 1, 4, 6, 8; A&S 1,2,3; A 1, 4 | $230,000 plus donors One-time dollars | AY 2012-13: summer 2013 | Design and Construction |  |  |
| c. Ventilation improvements to art history lecture room | USO 1, 4, 6, 8; A&S 1,2,3; A 1, 4 | $100,000 One-time dollars | AY 2013-14: summer 2014 | Design and Construction |  |  |
| d. Ventilation improvements to photography and prints , new wing roof repairs, work to emergency electrical system; electrical work in sculpture | USO 1, 4, 6, 8; A&S 1,2,3; A 1, 4 | $400,000 One-time dollars | AY 2013-14: summer 2014 | Design and Construction |  |  |
| e. Remodeling, wall insulation, roof repair, new windows and HVAC to old wing | USO1,4,6,8; A&S1,2,3 | $5 million | AY 2013-15 | Capital Planning, A&S Dean, Donors |  |  |
| Develop plan for studio technology such as iPads, cameras, projectors in studios | USO 1; A6 | To be determined | AY 2013-14 | Division chairs, faculty, Director, Dean, ITS |  |  |
| 6. Rebuild strategically administrative staff |  |  |  |  |  |  |
| a. Replace School of Art technician position | USO 1,4; A1,2,5 | $45,000 | AY 2012-13 | Dean, Provost |  |  |
| Create new shared administrative staff position to support public relations, and gallery operations | USO 3,5, 6; A1,2,4 | $40,000 | AY 2012-13 | Dean, Provost |  |  |
| Create new coordinator position shared with Theatre and Film (and Musical Arts) for digital technology | USO 1,4; A1,2,5 | $45,000 | AY 2012-13 | Dean, Provost |  |  |
| d. Create new part-time grant proposal writer position | USO 5; A3 | $20,000 | AY 2012-13 | Dean, Provost |  |  |
| 7. Continue to build partnerships (link to curriculum, scholarship of engagement) |  |  |  |  |  |  |
| Create new inter-institutional partnerships through which to recruit potential students | USO2; A3 | $10,000 marketing and travel for recruiting | 2012-15 | Director Faculty meeting reports |  |  |
| Strengthen collaboration with the Toledo Museum of Art and Arts Commission | USO1,3,4; A3 | $10,000 Grant proposal writing | 2012-15 | Director Faculty meeting reports |  |  |
| Increase external funding from donors and Corporations. | USO5; A1 | See fundraising priorities, Appendix G | 2012-15 | Faculty, Director, Development staff, Dean |  |  |
| e. Increase external funding from grant agencies | USO5; A1 | None, grant proposal writer in place | 2012-15 | Faculty, Director, Grant proposal writer |  |  |
| f. Strengthen collaborative cultural offerings in the arts | USO1,3; A1,2,3 | Donor support | AY 2012-16 | Chair, Director, Deans, Provost, CFO |  |  |
| 8. Continue to pursue visibility and economic development through the arts |  |  |  |  |  |  |
| a. Expand internship opportunities in graphic design, studio arts and art history | USO1,3; A1,3 | None | AY 2012-16 | Faculty and businesses |  |  |
| b. Increase reporting of faculty exhibitions /artworks/lectures/ workshops on campus | USO 4; A1,2,4 | None | AY 2012-15 | Faculty and businesses |  |  |
| c. Expand PR: press releases, TV marketing, DVDs, promotional information pack, PR internships | USO 6; A4 | None, if marketing specialist appointed | AY 2012-16 | Faculty, Marketing and Communications |  |  |
| d. Keep consistent identity between web and printed materials | USO 6; A4 | Marketing specialist, interns | AY 2012-15 | Faculty, Marketing and Communications |  |  |
| e. Conduct updated economic impact study of the arts funded by partner organizations | USO 3; A3 | $20,000 | AY 2012-13 | CRD, OCA, TACL0 |  |  |
| f. Continue and expand 3d printing research, review in 2013-14 | USO 3; A1,3 | Graduate assistant support | AY 2012-14 | Faculty, graduate student and staff |  |  |  |
| 9. Continue to collaborate among the arts |  |  |  |  |  |  |
| Develop new curricula in collaboration with the College of Musical Arts, Department of Theatre and Film and Creative Writing Program | USO 1,2,4,6; AS 1,2,3 | None | AY 2013-18 | Chair, Director, Dean, Provost, CFO | ASDM 22. 23, 24 |  |

NOTES ON PLANNED ACTIONS

Action 1

Successful NASAD reaccreditation.

Obtain facilities improvements and faculty and staff hires as below; complete NASAD self study in partnership with Interior Design Program, and VCT program if appropriate; conduct successful NASAD visit.

Action 2

Tenure-track faculty, rebuild to strengthen retention and regional engagement

Convert instructor (NTTF) lines to tenure-track (TTF) lines: the School of Art TTF: NTTF ratio in 2012-13 was 27:18 or 61:39, in 2010-11 was 24:19 or 56:44, in 2011-12 is 26:20 or 56:44, and in still below the College of Arts and Sciences goal of 75:25. Discussion of priorities 1-5 carried over from 2009 continues. Additional costs reallocated from vacant lines.

1. Tenure-track Associate Professor position, art education ($60,000, pos. no. 5217, Catalano, additional cost $9,256)

Strengthen teaching in new technologies and internships, leadership in education (USO 2, 20)

2. Tenure-track position, graphic design ($55,000, pos. no. 4693, Davis, reallocate surplus to Priority 1.)

3. Tenure-track position, 3-D intermedia ($50,000, pos. no. 5580, Maw, additional cost $5,670)

Strengthen teaching in new technologies and internships (USO 2, 20) and

4. Tenure-track position 2-D intermedia ($50,000, pos. no. 5682, Kumar, additional cost $2,316)

Strengthen teaching in new technologies and internships (USO 2, 20)

5. Tenure-track position, art history (Contemporary Art), (pos. no. 00005091, Durham formerly Duszynski, additional cost $15,000)

6.  Visiting Assistant Professor, visiting artist/scholar/critic in new media, converted instructor line (additional cost $10,000)

Strengthen teaching in new technologies, internships and writing (USO 2, 20)

7. Retain remaining instructor lines to improve access, if enrollments permit; strengthen quality and provide economic leadership

(see Appendix A, with all – new and renewed - instructor lines listed)

Action 3

Recruit to selectively grow student numbers in undergraduate and graduate programs

1. Grow School of Art enrollments to about 750-800 if resources remain stable; increase freshman enrollee quality and diversity by 5% to strengthen and broaden retention (5% increase in average portfolio and entering ACT scores); increase enrollment of non-traditional students by 5% in five years (number of students); increase diversity by 5% in five years (total degrees awarded to minority students); increase international students by 5% in five years (total degrees awarded)

2. Maintain current level of funding, increase number of graduate student stipends by two by partnering with other campus units

3. Increase fee-paying graduate students by 10% by reviving MFA in Graphic Design, $5,000 for recruitment materials

4. Contribute to University’s and Arts and Sciences recruitment, retention and graduation rates, seek half-time shared position of freshman/sophomore BFA advisor

5. Create scholarships for under-represented groups

Action 4

Build innovative curricula

- Create Intermedia curriculum.

2. Establish donor fund for team teaching, one class per semester.

3. Add contemporary art/criticism/theory class for all majors

4. Support faculty development for teaching with technology

5. Expand immersive learning: Study Abroad

6. Expand school-wide field trips – four per year

7. Create online learning communities

8. Expand curricular cultural diversity requirements

Action 5

Improve physical space, facilities and equipment

Priorities all fulfill USO 8 and comprise those carried over from last year and new ones emerging from current discussions in preparation for NASAD accreditation. Discussion will continue into the next budget biennium.

1. Remodeling of entire old wing of the School of Art including: NASAD accreditation related works comprising all items in 2 – 5 below; roof repair, new double-glazing, new wall insulation and finishes, HVAC repair/replacement and insulation; capital campaign item if appropriate. If not possible, then remodeling to be broken down as follows:

2. NASAD accreditation health and safety-related and other works to new and old wing: ventilation in and gas supply to relocated jewelry and metals studios, FAC 1102, 1104, 1106, carried over; remodeling FAC 1024, 1030, 1231 area and 112, new. Total cost, $400,000, revised cost $230,000, carried over (original estimate attached, revised estimate underway)

3. Replacement of HVAC system, FAC 204, carried over;

4. Replacement of HVAC in photography and printmaking studios, FAC 1203 – 1215 and 1219 – 1231, repair/installation of roof flashings, FAC 150, 200, carried over, estimate, relocation of emergency electrical system, FAC 1228, $400,000, carried over (estimate attached);

5. Remodeling of rest of old wing: roof repair, new double-glazing, new wall insulation and finishes, HVAC repair/replacement and insulation; capital campaign item if appropriate.

6. Develop plan for studio technology such as iPads, cameras, projectors in studios

Action 6

Rebuild staff to expand external resources, economic development and support new media

1. Fill current vacant technician position ($45,000)

1. Shared Secretary I, hire into current vacant position (return of Ducat UESP funds) to address donor and external relations, event planning and gallery operations.

2. Digital technician, share with Department of Theatre and Film to serve digital needs (new line $50,000)

3.  K-12 outreach and grant proposal writer, hire across arts units to serve community needs (new line, $20,000)

4. BFA Advisor, new line ($40,000)

Action 7

Continue to build partnerships

1. Create new inter-institutional partnerships from which to recruit potential students

2. Strengthen collaboration with the Toledo Museum of Art and Arts Commission

3. Increase external funding from donors and corporations

4. Increase external funding from grant agencies

5. Strengthen collaborative cultural offerings in the arts in the Wolfe Center and the community

Action 8

Continue to pursue visibility and economic development through the arts

1. Expand internship opportunities in graphic design, studio arts and art history

2. Increase faculty exhibitions /artworks/lectures/ workshops on campus

3. Expand PR: press releases, TV marketing, DVDs, promotional information pack, PR internships

4. Keep consistent identity between web and printed materials

5. Conduct updated economic impact study of the arts funded by partner organizations

6. Continue rapid prototyping research, review in 2013-14

Action 9

Continue to collaborate among the arts

1. Develop new curricula in collaboration with the College of Musical Arts, Department of Theatre and Film and Creative Writing Program

SCORECARD OF KEY MEASURES

(* = percentage of students, not degrees, ** IR data incomplete, *** total endowed and spendable)

| University System of Ohio Defined Measures | Related Items | Target Level | Five Year History | Other Bnchmrk |
| --- | --- | --- | --- | --- |
| Index | Title | Strategies | Actions |  | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 |  |
| USO 01 | Access: Post-secondary enrollment |  |  |  |  |  |  |  |  | N/A |
| USO 1a | Access: Post-secondary enrollment (Total) | A 2 | Work w/ Admissions | 5% BFA 25% 3D | 700? | 773? | 788? | 697 | 671 |  |
| USO 01b | Access: Post‐secondary enrollment (Undergraduate) | A 2 | Work w/ Admissions | 750 | 678? | 750? | 769? | 673 | 647 |  |
| USO 01c | Access: Post‐secondary enrollment (Graduate) | A 2 | Work w/ Admissions | 22+ 3 fee-paying | 22 | 23 | 27 | 24 | 22 |  |
| USO 03a | Access: Total enrollees 25 & older | A 2 | Work w/ Admissions | No data, cannot set | n/a | n/a | 9% | n/a | n/a |  |
| USO 03b | Access: Total enrollees 25 & older (Undergraduates) | A 2 | Work w/ Admissions | No data, cannot set | n/a | n/a | 7% | n/a | n/a |  |
| USO 03c | Access: Total enrollees 25 & older (Graduates) | A 2 | Work w/ Admissions | No data, cannot set | n/a | n/a | 66% | n/a | n/a |  |
| USO 04 | Access: Total Degrees to 1st generation students | A 2 | Work w/ Admissions | No data, cannot set | n/a | n/a | n/a | n/a | n/a |  |
| USO 05 | Access: Total Degrees to Black & Hispanic students | A 2, 7 | Work w/ Admissions | No data, cannot set | 6.5%* | n/a | 8%* | n/a | n/a |  |
| USO 06a | Quality: Improvement in actual rate over expected graduation rate (2007 as baseline) total improvement | A 2 | Work with A&S and SoA advisors | No data, cannot set | n/a | n/a | n/a | n/a | n/a |  |
| USO 06b | Quality: Improvement in actual rate over expected graduation rate (2007 as baseline) undergrad improvement | A 2 | Work with A&S and SoA advisors | No data, cannot set | n/a | n/a | n/a | n/a | n/a |  |
| USO 06c | Quality: Improvement in actual rate over expected graduation rate (2007 as baseline) graduation improvement | A 2 | Work with A&S and SoA advisors | No data, cannot set | n/a | n/a | n/a | n/a | n/a |  |
| USO 07 | Quality: Average ACT score of entering students | A 2 | Work with Admissions | 5% increase = 24.15 | 22.26 | n/a | 23 | n/a | n/a |  |
| USO 08 | Percentage of facilities in satisfactory condition or needing only minor rehabilitation | A 5 | Work with A&S Advancement, Capital Plannng | 100% | n/a | See university master plan | See university master plan | See university master plan | See university master plan |  |
| USO 09 | Total size of endowments and foundations (per FTE)*** | A 5 | Work with A&S Advancement | 5% increase | $669,765 ($957) | $758,000 ($974) | n/a | $922,377 ($1323) | $1,490,000 ($2200) |  |

| University System of Ohio Defined Measures | Related Items | Target Level | Five Year History | Other Bnchmrk |
| --- | --- | --- | --- | --- |
| Index | Title | Strategies | Actions |  | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 |  |
| USO 14 | Percentage of first time enrollees below age 21 with equivalent of one semester or more of college credit earned during high school | A 2 | Gather data, work with Admissions | No data, cannot set | n/a | n/a | n/a | n/a | n/a |  |
| USO 15 | Percentage of bachelor’s degree recipients with at least one year of credit from a community college | A 2 | Gather data, work with Admissions | No data, cannot set | n/a | n/a | n/a | n/a | n/a |  |
| USO 17 | Globalization measure: Total international students/Ohio students studying abroad annually | A 7 | Add to capital campaign & work with CFO | 2%/3% | Unknown/2% | 1%/2% | n/a | n/a | n/a |  |
| USO 19 | Invention disclosures filed and university start ups attracting more than $1 million | A 3 | Work with VP for Research | 2 | 2 | 0 | 0 | 0 | 3 |  |
| USO 20 | Number of students engaged in internships and co-ops | A 3 | Work with partners | 5% (40) | n/a | n/a | 3% 24 (est.) | 3% 26 (est.) | 3% 28 (est.) |  |

** IR data incomplete  *spring semester numbers

| University/College Defined Measures | Related Items | Target Level | Five Year History | Other Bnchmrk |
| --- | --- | --- | --- | --- |
| Index | Title | Strategies | Actions |  | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 |  |
| ASDM1 | % Tenure track faculty v. Non‐TTF | Hire more TTF AS 1, A 5 | Seek more TTF/convert existing lines | 75:25 | 61:39 (28 TT: 18 NTTF) | 56:44 (24 TT:19 NTTF) | 56:44 (24 TT:19 NTTF) | 56:44 (26 TT:20 NTTF) | 55:45 (26 TT:21 NTTF) |  |
| ASDM4 | Enrollment numbers by Department | Grow BFA 3D; USO 1, A 2 | Work with admissions | 25% growth in 5 years | n/a | n/a | n/a** | 27 | 38 |  |
| ASDM10 | Support interdisciplinary initiatives | ARTSX; USO 7, A 5 | formalize | Expand to Wolfe and Moore | n/a | n/a | n/a | n/a | Expanded to Wolfe |  |
| ASDM 12 | Increase students participating in study abroad programs | Fundraise | Add to capital campaign | 50% increase | 2% (11) | 2% (14) | 2% (13) | Minus 33% (9) | n/a |  |
| ASDM 22 | Enrollment in Arts related majors | Increase quality | Work with admissions | 5% increase = 24.15 | 22.26 | n/a | 23 | n/a | n/a |  |
| ASDM 23 | Graduation numbers in Arts related majors | Increase BFA Art Ed &3D only | Increase enrollments | 5% increase | n/a | n/a | n/a** | n/a | n/a |  |
| ASDM 24 | Attendance numbers at Arts related functions | Marketing staff | Seek approval | 100% increase | n/a | n/a | n/a | n/a | n/a |  |

SCORECARD OF KEY MEASURES

(issues not yet addressed, or new problems post 2004 accreditation renewal; *targets levels are  NASAD 2010 averages from public institutions with 401+ majors)

| Externally Defined Measures (NASAD) | Related Items | Target Level* | Five Year History | Other Bnchmrk |
| --- | --- | --- | --- | --- |
| Index | Title | Strategies | Actions |  | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 |  |
| NASAD 1b | Size and Scope: academic faculty budget, Ratio (TTF:NTTF) | Convert NTTF to TTF | Seek more TTF positions; grow salaries | 75:25 | 61:39 (28 TT: 18 NTTF) | 56:44 (24 TT:19 NTTF) | 56:44 (24 TT:19 NTTF) | 56:44 (26 TT:20 NTTF) | 55:45 (26 TT:21 NTTF) |  |
| NASAD 1c | Size and Scope: graduate student resources | Grow funded & fee paying | Partial assts, grow GD MFA | 22/unknown | 18/8 self funding | 21/4 self funding | 18/9 self funding | 19/6 fee paying | 22/0 paying |  |
| NASAD 1d | Size and Scope: administrative and technical resources | Add secretary and dig. tech | Return UESP, tech w/ THFM | 16.45 FT positions | 8 | 8 | 7.6 | 6.5 | 8.5 |  |
| NASAD 1e | Size and scope: provision for general education | Retain sections | Include in CUE | No NASAD measures | 12 | 16 | 15 | 18 | 7 |  |
| NASAD 1f | Size and Scope: non-personnel budget (lab and usage fee) | Up operating & usage fee | Add art fee/up usage fee | $800,000 | $428,000 | $483,000 | $750,000 | $232,000 | $222,000 (to date) |  |
| NASAD 1g | Size and Scope: Fundraising (size of endowments) | Add SoA to new campaign | Work with Advancement | No NASAD measures | $669,765 | $758,000 | $831,000 | $831,000 | $1,290,000 |  |
| NASAD 2 | Facilities, equipment and safety | Move metals, renovate new and old wing, | Work with A&S/Capital | NASAD curriculum quality | $350,000 | $500,000 | 0 | 0 | $230,000/ $600,000 |  |
| NASAD 3 | Recruitment, retention, record-keeping, advisement | Add secretary | Return UESP (see 1d above) | 1 FT | 2 | 2 | 1 | 1 | 1.5 |  |

| School of Art Defined Measures | Related Items | Target Level | Five Year History | Other Bnchmrk |
| --- | --- | --- | --- | --- |
| Index | Title | Strategies | Actions |  | 2008-09 | 2009-10 | 2010-11 | 2011-12 |  |  |
| SoADM1 | Academic faculty budget Ratio (TTF:NTTF) | Convert NTTF to TTF | Seek new and convert TTF positions | 75:25 | 61:39 (28 TT: 18 NTTF) | 56:44 (24 TT:19 NTTF) | 56:44 (24 TT:19 NTTF) | 56:44 (26 TT:20 NTTF) | 55:45 (26 TT:21 NTTF) |  |
| SoADM2 | Facilities, equipment and safety: value of construction work, status of space (percentage of poor, fair, good) | Move metals, renovate FAC, | Work with A&S/Capital Planning | $600,000 | $350,000/ n/a | $500,000/ n/a | 0/ n/a | 0/ n/a | $230,000/600,000 |  |
| SoADM3 | Graduate student resources | Grow assistantships & fee payers | Retain level funding, grow GD MFA | 21/10 fee paying | 18/8 fee paying | 21/4 fee paying | 18/9 fee paying | 19/6 fee paying | 22/0 fee paying |  |
| SoADM4 | Administrative and technical resources | Add secretary and dig. tech | Return UESP, tech w/ THFM | 11 positions | 8 | 8 | 7 | 6.5 | 8.5 |  |
| SoADM5 | Quality: Average portfolio and ACT scores of freshman BFA students | Increase | gather data & offer wkshps | tbd | n/a | n/a | n/a | n/a | n/a |  |
| SoADM6 | Number of students engaged in practicums, internships and co-ops | Increase | Work with regional ptnrs | 5% (40) | n/a | 28 | 36 | 37 | 39 |  |

Appendix A – Instructor Searches/Renewals for 2013-14

Art Education

Teacher prep (renewal requested, instructor awaiting promotion to lecturer, Sheets), USO 6, 20

Teacher prep (renewal to be requested, Vanden Eynden), USO 6, 20

Art History

Beginning and intermediate art history (renewal requested, lecturer, Light), USO 2

Beginning and intermediate art history (renewal requested, Durham), USO 2

2-D Studies

Drawing/Painting (renewal to be requested, Briggs) USO 6

Photography, digital (renewal requested, Leonard, J.), USO 2, 6

Printmaking (search underway, Kenar position), USO 2, 6

Digital (Smith, terminal contract-hold position for Kumar tenure-track line, see tenure-track plans), USO 2

3-D Studies

Ceramics (renewal requested, Leonard C., Balistreri FIL replacement), USO 2, 6

Ceramics (renewal to be requested, Beiner) USO 2, 6

Glass (renewal to be requested, Newbold), USO 6

Jewelry/metals (renewal to be requested, Kuebeck), USO 2, 6,

Sculpture (renewal to be requested, Lock), USO 2, 6

Digital Arts

Animation (renewal requested, Somasa), USO 2, 6

Imaging (renewal requested, Madsen, Mitchell 2013-14 FIL replacement), USO 2, 6

First Year Program

2-D (renewal requested, Dupay), USO 6

3-D (non-renewal due to lower enrollments, Garber Pearson)

2-D (Renewal requested, Fontana), USO 2, 6

Graphic Design

Renewal to be requested, Shelley, USO 2, 6

Renewal requested, lecturer, Fidler, USO 2, 6

(Please note School of Art TTF: NTTF ratio in 2010-11 was 24:19 or 56:44, in 2011-12 was 26:20 (56:44), and in 2012-13 is expected to be 26:21 (55:45), below the College of Arts and Sciences goal of 75:25).

INDEX OF APPENDICES

It is anticipated that additional documentation may be useful in providing context to this submission.  Each unit is required to complete a SWOT analysis (Strengths, Weaknesses, Opportunities, Threats), summary of results of prior year’s action plans, review of program level assessment reports, reconciliation of funds from open faculty lines, and a listing of any external rankings.  Additional documentation to support the strategic plan should also be included.

- Appendix A: SWOT (required). Attached.

- Appendix B: Summary of results of prior year’s action plans (required). Attached.

- Appendix C: Review of Program Level Assessment Reports – This narrative should summarize the results of the assessment reports and any appropriate action planned (required). Attached.

- Appendix D: Funds available from open faculty lines and projected use of these funds (required).  Attached.

- Appendix E: Where appropriate, external rankings of programs (required). Digital Arts, top 8 in Midwest, School of Art US News and World ranking of graduate program at 114, reputation largely based on size of graduate programs.

- Appendix F: Facilities and Infrastructure (Short-term and long-term facility needs) Estimates for:

- Accreditation related works: Attached are i) F-BGSU – Fine Arts Study MEP 12.6.11.pdf;

ii) F-Fine Arts Renov Estimate_11-10-25.pdf; will be updated for revised budget allocation

iii) F-Fine Arts Bldg_11-12-05.pdf; will be updated for revised budget allocation

- Ventilation issues in Photo, printmaking and ceramics: 10029 Fine Arts Study Rev 001.pdf

- Electrical and ventilation works in ceramics and sculpture: i) FAA 1112.pdf and ii) FAA 1218.pdf

7.    Appendix G: Fundraising Plan SoA fundraising priorities 12-11-05