Event Checklist and Budget Estimate Sheet

Organized by:___________________________________________________________________________________

Telephone ______________________________ (daytime) ______________________________________ (evening)

Mailing address _________________________________________________________________________________

Email address ___________________________________________________________________________________

Event name: ____________________________________________________________________________________

Purpose: _______________________________________________________________________________________

Target audience: _________________________________________________________________________________

Date: ___________________________________________________Time: __________________________________

Location/Venue: _________________________________________________________________________________

Expected attendance: ___________________                        Admission price: $___________________/per person

ESTIMATED TOTAL INCOME:  $___________________

Projected Expenses:

Facilities/room rental charges 								$___________________

Set-up charges/fees 									$___________________

Rental equipment (includes audio-visual, tents, risers, tables, chairs, etc.) 		$___________________

Food 											$___________________

Beverages 										$___________________

Bartender fees/gratuities 								$___________________

Promotional materials (printing & mailing of invites, signage, programs, flyers, etc.) 	$___________________

Decorations 										$___________________

Entertainment 										$___________________

Transportation (buses, vans, parking, valets, and gratuities for drivers, etc.) 		$___________________

Miscellaneous (includes plaques, photos, speaker travel/expenses, and supplies, etc.) 	$___________________

ESTIMATED TOTAL EXPENSES: $___________________

Projected Profit:  $___________________

Other alumni volunteers who will assist with the event:

1) ________________________________ 		4) ________________________________

2) ________________________________ 		5) ________________________________

3) ________________________________ 		6) ________________________________

EVENT PLANNING CHECKLIST

12 or More Weeks before the Event

- Confirm the event date with BGSU Alumni Office and set an RSVP date

- Complete Planning Worksheet and send to the Alumni Office

- Outline event, including goals, objectives, guest speaker, etc.

- Assign responsibilities

- Establish event budget, including facility rental, food and supplies, decorations, printed materials, A/V equipment, door prizes, gratuities, etc.

- Calculate per-person event costs

- Contact BGSU Alumni Office for mailing and publicity assistance

10 or More Weeks before the Event

- Select and reserve location. Things to consider:

- Is there convenient and adequate parking?

- Is there an acceptable billing arrangement?

- Is the room size appropriate for the anticipated crowd?

- Is the noise level appropriate if you have a speaker?

- Reserve A/V equipment, if needed

- Set menu and arrange for bar service, if appropriate

- Contact BGSU Alumni Office if the event includes a fundraising element

Eight Weeks before the Event

- Determine volunteer staffing needs (ex- greeters, name tag table attendant, food servers, clean-up crew, etc.)

- Recruit members to staff the event

- Notify BGSU Alumni Office of any special needs for the event

- Forward event information to BGSU Alumni Office for email blast and social media inclusion

Six Weeks before the Event

- Mail printed invitations (if needed)

- Order/purchase door prizes and other supplies

Three-Four Weeks before the Event

- Work with BGSU Alumni Office to finalize publicity

- BGSU Alumni sends email for event

Two Weeks before the Event

- Call members who have not responded

- Your group and BGSU Alumni Office publicize event through social media

One Week before the Event

- Prepare registration materials and name tags

- Provide final count to facility managers and caterers, as needed

- Send list of attendees to BGSU Alumni Office

EVENT PLANNING CHECKLIST (cont.)

Two days before the Event

- Send email reminder to registrants

Day of the Event

- Arrive 1-2 hours prior to event to make sure facility is arranged properly

- Set up registration table and name tags

- Recognize guests and speakers

- Distribute event evaluations, and collect them when completed

- Take photos!

Following the Event

- Mail thank-you notes to attendees and helpers

- Submit photos electronically to the BGSU Alumni Office

- Send list of final attendees to BGSU Alumni Office

- If event included fundraising, contact the BGSU Alumni Office

Questions? Contact Sarah at the BGSU Office of Alumni at 419-372-0352 or sbrokamp@bgsu.edu.